## Sheet1
Tool Number : |  |  | II71 |  |  |  | Section : |  | IMPLANT
Location(s) : |  |  | 4 | 0.S55 | [8 empty] | 363
Tool owner : |  |  |  | Iwan van der Wielen |  |  | Tel no : |  | 06-12963144
Facilities Project leader: | [6 empty] | Tel no : | [5 empty] | 363
Step No. | Action: Decommisioning ICN6 | [7 empty] | Planned Date | Checked by (sign and date)
1 | Overview of fixed connections | [11 empty] | N2
| Vul onderstaande lijst van vaste aansluitingen in, indien het apparaat uit meerdere modules bestaat maak dan een beschrijving per module. | [11 empty] | N2
Een overzicht van vaste aansluitingen staat in bijlage 2.
|  |  | Name |  | VARIAN |  | (Branch) code
| Module 1 : |  | HIGH CURRENT IMPLANTER |  | E220HP | [5 empty] | gecorrigeerd | [5 empty] | if not according list please give comment.
(name toolowner)
Connection
|  |  | Main unit |  | Stramien F-K/20-21 |  | Dry Compressed Air | PN |  |  | Main unit | Stramien F-K/20-21 |  | Dry Compressed Air | PN
|  |  | Main unit |  | Stramien F-K/20-21 |  | Nitrogen w/o Purifier | N2 |  |  | Main unit | Stramien F-K/20-21 |  | Nitrogen w/o Purifier | N2
|  |  | Main unit |  | Stramien F-K/20-21 |  | Process Cooling Water | CW3 |  |  | Main unit | Stramien F-K/20-21 |  | Process Cooling Water | CW3
|  |  | Main unit |  | Stramien F-K/20-21 |  | Exhaust - General | General |  |  | Main unit | Stramien F-K/20-21 |  | Exhaust - General | General
|  |  | Main unit |  | Stramien F-K/20-21 |  | Exhaust - Scrubbed | Scrubbed |  |  | Main unit | Stramien F-K/20-21 |  | Exhaust - Scrubbed | Scrubbed
|  |  | Main unit |  | Stramien F-K/20-21 |  | ENP208 | ENP208 |  |  | Main unit | Stramien F-K/20-21 |  | ENP208 | ENP208
2 | Overview of contaminations present inside the tool and information on how these contaminations have been removed | [8 empty] | (name toolowner)
If a part of the tool cannot be cleaned inside the cleanroom, write down clearly : what package, what waste number flow, and the name of the company that will treat the contaminated part / waste.
| tool part | contamination |  | how to clean this part | [5 empty] | Agreed by
| Vacuum pumps | Boron, Phosfor, Arsenic |  | Overhaul at supplier | [5 empty] | ESH Contact Persoon
| Vacuum tubes | Boron, Phosfor, Arsenic |  | Cleanpart
| Assembly's | Boron, Phosfor, Arsenic |  | Overhaul in ICN8 Basement (Applied)
| - | - |  | -
| - | - |  | -
| tool part | contamination |  | waste number flow, package, company | [10 empty] | Count of Main_Tool
|  |  |  | - | [10 empty] | Main_Tool | Total
| - | - |  | - | [10 empty] | BA03 | 1
| - | - |  | - | [10 empty] | BA30 | 3
| - | - |  | - | [10 empty] | BA31 | 3
| - | - |  | - | [10 empty] | BA60 | 6
| - | - | [12 empty] | BA62 | 6
3 | Risk assessment has been made and measures have been defined in order to minimize hazardous effects and risks. | [8 empty] | Agreed by |  |  |  |  | BA63 | 6
[10 empty] | (Section manager) |  |  |  |  | BT01 | 8
[15 empty] | BT04 | 8
[15 empty] | BT07 | 8
[10 empty] | Agreed by : |  |  |  |  | BT10 | 8
[10 empty] | (ARBO Contact Person) |  |  |  |  | BT13 | 9
4 | The tool-removal-roadmap-plan has been reported to and approved by steering committee Constructions, Equipment Infrastructures and Facilities ICN6. | [8 empty] | (name leader steering committee) |  |  |  |  | CD01 | 9
5 | Pictures have been taken of tool and its connections. | [8 empty] | (name toolowner) |  |  |  |  | CD02 | 9
6 | Tool status in FMMS / ERIC is 'down' and notification forms have been attached saying the tool cannot be used anymore. | [8 empty] | (name toolowner) |  |  |  |  | CF23 | 5
7 | All chemical sources - gasses , as well as liquids , as well as solid chemicals - have been removed out of the tool. | [8 empty] | (name toolowner) |  |  |  |  | DC01 | 6
8 | All chemical inputs have been rinsed well starting from VMB connection point. Connection points have been closed and sealed both at VMB and at tool. | [8 empty] | name BASF employee) |  |  |  |  | DR04 | 5
9 | Bulk gas, as well as non-bulk gas connections have been rinsed well starting from VMB connection, closed and sealed. Exceptions here are N2 and compressed air | [8 empty] | (name Air Products employee) |  |  |  |  | EA11 | 35
10 | Connectors, pumps, filters and process chambers have been rinsed well, according to acceptabel rest value analysis / tests. | [8 empty] | (name toolowner) |  |  |  |  | EA21 | 25
11 | Tool has been labeled with clear information about contamination status : 'tool is clean', or 'the following contaminants are still present : ....' ; add waste treatment flow numbers if applicable. | [8 empty] | (name toolowner) |  |  |  |  | EA31 | 26
12 | Demi water flow has been disconnected, connectors removed and connector ends blocked. | [8 empty] | (name facilities projectleader) |  |  |  |  | EA41 | 26
| (Be aware of impacts upon branch !). | [13 empty] | EE55 | 30
13 | Tool has been prepared and is ready for deconnection of electrical power and other facilities | [8 empty] | (name toolowner) |  |  |  |  | FS61 | 24
14 | Electrical power has been shut down and deconnected. | [8 empty] | (name facilities projectleader) |  |  |  |  | FS62 | 24
15 | All fixed connections have been removed from tool and blocked at branch level. Exhaust has been re-adjusted if applicable.. | [8 empty] | (name facilities projectleader) |  |  |  |  | FS63 | 24
16 | Tool can be moved out of the cleanroom. | [8 empty] | (name toolowner) |  |  |  |  | FS64 | 23
| Describe here the plan of removal and what will be the end situation of removal. | [13 empty] | FS65 | 22
| If contaminated parts are still present please describe here how the transfer of these parts is done | [13 empty] | GK52 | 3
17 | Describe here what will be the future of the removed tool ,like : scrapped, to be sold, put in stock waiting for customer, re-install, etc. | [8 empty] | (name toolowner) |  | 1 |  |  | II71 | 6
18 | The tool-removal-roadmap-and-data-book is handed over to project leader. | [8 empty] | (name facilities projectleader) |  |  |  |  | II72 | 7
| (Make a copy) | [13 empty] | II73 | 7
19 | Cleanroom floor has been cleaned by : (Name cleaning firms) | [8 empty] | (name toolowner) |  |  |  |  | II81 | 7
[15 empty] | II82 | 7
| Note : The removal of loose parts will not be done by cleaning firms, but clearly must be done by the person who actually removed the part. | [13 empty] | II83 | 7
| choose : Lavold , in case of not contaminated floor | [13 empty] | II84 | 6
| choose: Recontec, in case of contaminated floor | [8 empty] | (name facilities projectleader) |  |  |  |  | KPT1 | 1
20 | Clean room floor parts (tiles) have been restored (renewed). | [8 empty] | (name facilities projectleader) |  |  |  |  | KPT2 | 1
21 | Owners of all shop floor control systems have been informed. | [13 empty] | KPT3 | 1
| Make a list of relevant systems below here : | [13 empty] | KPT4 | 1
[15 empty] | LE61 | 2
[15 empty] | LE81 | 2
[15 empty] | MD10 | 16
[15 empty] | MP01 | 4
[15 empty] | MP11 | 1
[15 empty] | MP12 | 1
| System |  |  |  |  | Owner |  | Done | [6 empty] | MP15 | 2
| des-investment laid down at Picnic by RNP-N60/P00-12 . |  |  |  |  | EPE | [8 empty] | MP16 | 1
| Inventory number |  |  |  |  | F&A | [8 empty] | MP17 | 1
| Site model |  |  |  |  | IT&A | [8 empty] | MP31 | 2
| Operation sheets, maintenance sheets, recipes documents, FMEA, process control charts (Cpk) etc. |  |  |  |  | EPE | [8 empty] | MP32 | 1
| Electric connection |  |  |  |  | Facilities | [8 empty] | MP33 | 2
| Usage model chemicals |  |  |  |  | Facilities | [8 empty] | MP34 | 2
| Equipment facilities matrix |  |  |  |  | Facilities | [8 empty] | MP35 | 3
[10 empty] | (name toolowner) |  |  |  |  | MP38 | 3
22 | Succesful tool removal has been reported at steering committee Constructions, Equipment Infrastructures and Facilities ICN6. | [8 empty] | (name leader steering committee) |  |  |  |  | MP41 | 3
23 | A copy of the tool-removal-roadmap-and-data-book has been archived. | [8 empty] | (name toolowner) |  |  |  |  | MP42 | 3
[15 empty] | MP43 | 3
[10 empty] | name facilities engineer) |  |  |  |  | MP45 | 3
[15 empty] | MP51 | 2
[15 empty] | MP52 | 1
[15 empty] | MP55 | 1
[15 empty] | MP72 | 2
[15 empty] | MP80 | 3
[15 empty] | MP81 | 3
[15 empty] | MP82 | 3
[15 empty] | MP83 | 3
[15 empty] | MP84 | 2
[15 empty] | MP85 | 3
[15 empty] | MP93 | 3
[15 empty] | MP95 | 8
[15 empty] | MP96 | 7
[15 empty] | MP99 | 1
[15 empty] | MS10 | 19
[15 empty] | MS20 | 18
[15 empty] | MS30 | 19
[15 empty] | MS40 | 11
[15 empty] | OT04 | 8
[15 empty] | OT07 | 8
[15 empty] | OT10 | 8
[15 empty] | OT13 | 8
[15 empty] | OT16 | 9
[15 empty] | OT19 | 9
[15 empty] | PL07 | 12
[15 empty] | PL08 | 22
[15 empty] | PL09 | 16
[15 empty] | PL10 | 19
[15 empty] | PL11 | 23
[15 empty] | PL12 | 23
[15 empty] | PL13 | 25
[15 empty] | PL14 | 24
[15 empty] | PL15 | 28
[15 empty] | PL16 | 28
[15 empty] | PL17 | 23
[15 empty] | PL18 | 24
[15 empty] | PL19 | 21
[15 empty] | PL20 | 21
[15 empty] | PL21 | 25
[15 empty] | PL29 | 11
[15 empty] | PL30 | 10
[15 empty] | PL31 | 11
[15 empty] | PL32 | 11
[15 empty] | PL33 | 8
[15 empty] | PL34 | 10
[15 empty] | PL35 | 10
[15 empty] | PL36 | 10
[15 empty] | PL68 | 8
[15 empty] | PL69 | 8
[15 empty] | PL70 | 8
[15 empty] | PR01 | 4
[15 empty] | PR03 | 4
[15 empty] | PR05 | 5
[15 empty] | RT01 | 7
[15 empty] | SD03 | 18
[15 empty] | SD04 | 21
[15 empty] | SD05 | 18
[15 empty] | SD06 | 21
[15 empty] | SD07 | 21
[15 empty] | SD11 | 3
[15 empty] | SD12 | 3
[15 empty] | SD13 | 3
[15 empty] | SD14 | 3
[15 empty] | SG10 | 2
[15 empty] | SG20 | 2
[15 empty] | SE01 | 13
[15 empty] | SE02 | 13
[15 empty] | SM01 | 6
[15 empty] | SM02 | 7
[15 empty] | ST01 | 3
[15 empty] | ST02 | 4
[15 empty] | ST03 | 3
[15 empty] | ST04 | 3
[15 empty] | ST05 | 3
[15 empty] | ST06 | 3
[15 empty] | ST07 | 3
[15 empty] | ST08 | 3
[15 empty] | ST09 | 3
[15 empty] | ST10 | 3
[15 empty] | ST11 | 3
[15 empty] | ST12 | 3
[15 empty] | ST13 | 3
[15 empty] | ST14 | 3
[15 empty] | ST15 | 4
[15 empty] | STK00 | 15
[15 empty] | STK01 | 15
[15 empty] | STK02 | 13
[15 empty] | STK03 | 14
[15 empty] | STK04 | 17
[15 empty] | STK05 | 14
[15 empty] | STK06 | 12
[15 empty] | STK07 | 17
[15 empty] | STK08 | 10
[15 empty] | STK11 | 8
[15 empty] | STKA01/02 | 2
[15 empty] | TDL01 | 2
[15 empty] | WB01 | 11
[15 empty] | WB02 | 13
[15 empty] | WB03 | 11
[15 empty] | WB04 | 10
[15 empty] | WB05 | 13
[15 empty] | WD10 | 50
[15 empty] | WM60 | 2
[15 empty] | WM61 | 2
[15 empty] | WME6 | 1
[15 empty] | WME8 | 1
[15 empty] | WME9 | 1
[15 empty] | WS01 | 1
[15 empty] | WS03 | 1
(blank)
[15 empty] | Grand Total | 1543